## MILESTONES
MILESTONES (Revised)
Global Cropland Area Database at 30 m resolution (GCAD30) Project: June, 2013- May, 2018
NASA MEaSUREs
PI: Prasad S. Thenkabail. U. S. Gelopgical Survey, Flagstaff, AZ; pthenkabail@usgs.gov
Tel.: 928-380-9965
| 2013 | 2013 | 2013 | 2013-2014 | 2014 | 2014-2015 | 2015 | 2015-2016 | 2016 | 2016-2017 | 2017 | 2017-2018
| 2013-06-01 | 2013-06-01 | 09/01/2013 to 05/28/2013 | 12/01/2013 to 02/28/2014 | 03/01/2014 to 08/31/2014 | 09/01/2014 to 02/28/2015 | 03/01/2015 to 08/31/2015 | 09/01/2015 to 02/29/2016 | 03/01/2016 to 08/31/2016 | 09/01/2016 to 02/28/2017 | 03/01/2017 to 08/31/2017 | 09/01/2017 to 05/31/2018
A. Revised budget submission and approval from NASA
B. Project start date date
C. USGS agreements with co-Is
D. Staffing: post doctoral researcher, Research scientist start date
E. Staffing: 3 PhD students
F. Data storage, backup readiness in USGS Flagstaff: 70 terabytes
G. compter systems and software readiness in Flagstaff
H. Project initiation meeting
I. GLS2010 data mosaicking and organization
J. Very high resolution imagery acquisition
K. GLS1990 data normalization, mosaicking
L. Cropland extent algorithm refinement and implementation
M. Product 1: global cropland extent 2010
N. Product 2: global cropland extent 1990
O. existing in-situ field data harmonization
P. further in-situ field data collection and harmonization
Q. Product 3: Global ground data system ready
R. Cropland irrigation vs. rainfed delineation
S. Cropland irrigation vs. rainfed refinement and implementation
T. Product 4: Irrigated versus rainfed croplands of the world 2010
U. Product 5: Irrigated versus rainfed croplands of the world 1990
V. Crop type identification and labeling (major 4 to 8 crops)
W. Crop type mapping algorithm refinement and implementation
X. Product 6: crop types (4 to 8 major) of the world 2010
Y. Product 7: crop types (4 to 8 major) of the world 1990
Z. Cropping intensities
AA. Crop intensity algorithm refinement and implementation
AB. Product 8: crop intensities (4 to 8 major) of the world 2010
AC. Product 9: crop intensities (4 to 8 major) of the world 1990
AD. Product 10: Global Maps: Uncertainty, errors, and accuracies 2010
AE. Product 11:Global Maps: Uncertainty, errors, and accuracies 1990
AF. Product 12: Global Cropland Area Database Area statistics
Products at this stage (below) go to LP DAAC
AG. Products 1, 4, 6, 8, 10: Final GCAD2010 product release after evaluations
AH. Products 2, 5, 7, 9, 11: Final GCAD1990 product release after evaluations
AI. Products 12: Final GCAD1990 product release after evaluations
AJ. Product 13: GCAD four decades product release
AK. Product 14: Web\data portal development and data dissemination
AL. workshop, broad dissemination, presentations, publicatiosn

## community-milestones
COMMUNIT MILESTONES (Revised)
Global Cropland Area Database at 30 m resolution (GCAD30) Project: June, 2013- May, 2018
NASA MEaSUREs
PI: Prasad S. Thenkabail. U. S. Gelopgical Survey, Flagstaff, AZ; pthenkabail@usgs.gov
Tel.: 928-380-9965
Products | 2013 | 2013-2014 | 2014 | 2014-2015 | 2015 | 2015-2016 | 2016 | 2016-2017 | 2017 | 2017-2018 | Community
| 06/01/2013 to 08/31/2013 | 09/01/2013 to 02/28/2014 | 03/01/2014 to 08/31/2014 | 09/01/2014 to 02/28/2015 | 03/01/2015 to 08/31/2015 | 09/01/2015 to 02/29/2016 | 03/01/2016 to 08/31/2016 | 09/01/2016 to 02/28/2017 | 03/01/2017 to 08/31/2017 | 09/01/2017 to 05/31/2018
M. Product 1: global cropland extent 2010 | [10 empty] | GEO, GEOGLAM, National Intitutes, International Institutes, LP DAAC, USGS, NASA SERVIR
N. Product 2: global cropland extent 1990 | [10 empty] | GEO, GEOGLAM, National Intitutes, International Institutes, LP DAAC, USGS, NASA SERVIR
Q. Product 3: Global ground data system ready | [10 empty] | GEO, GEOGLAM, National Intitutes, International Institutes, LP DAAC, USGS, NASA SERVIR
T. Product 4: Irrigated versus rainfed croplands of the world 2010 | [10 empty] | GEO, GEOGLAM, National Intitutes, International Institutes, LP DAAC, USGS, NASA SERVIR
U. Product 5: Irrigated versus rainfed croplands of the world 1990 | [10 empty] | GEO, GEOGLAM, National Intitutes, International Institutes, LP DAAC, USGS, NASA SERVIR
X. Product 6: crop types (4 to 8 major) of the world 2010 | [10 empty] | GEO, GEOGLAM, National Intitutes, International Institutes, LP DAAC, USGS, NASA SERVIR
Y. Product 7: crop types (4 to 8 major) of the world 1990 | [10 empty] | GEO, GEOGLAM, National Intitutes, International Institutes, LP DAAC, USGS, NASA SERVIR
AB. Product 8: crop intensities (4 to 8 major) of the world 2010 | [10 empty] | GEO, GEOGLAM, National Intitutes, International Institutes, LP DAAC, USGS, NASA SERVIR
AC. Product 9: crop intensities (4 to 8 major) of the world 1990 | [10 empty] | GEO, GEOGLAM, National Intitutes, International Institutes, LP DAAC, USGS, NASA SERVIR
AD. Product 10: Global Maps: Uncertainty, errors, and accuracies 2010 | [10 empty] | GEO, GEOGLAM, National Intitutes, International Institutes, LP DAAC, USGS, NASA SERVIR
AE. Product 11:Global Maps: Uncertainty, errors, and accuracies 1990 | [10 empty] | GEO, GEOGLAM, National Intitutes, International Institutes, LP DAAC, USGS, NASA SERVIR
AF. Product 12: Global Cropland Area Database Area statistics | [10 empty] | GEO, GEOGLAM, National Intitutes, International Institutes, LP DAAC, USGS, NASA SERVIR
Products at this stage (below) go to LP DAAC
AG. Products 1, 4, 6, 8, 10: Final GCAD2010 product release after evaluations | [10 empty] | GEO, GEOGLAM, National Intitutes, International Institutes, LP DAAC, USGS, NASA SERVIR
AH. Products 2, 5, 7, 9, 11: Final GCAD1990 product release after evaluations | [10 empty] | GEO, GEOGLAM, National Intitutes, International Institutes, LP DAAC, USGS, NASA SERVIR
AI. Products 12: Final GCAD1990 product release after evaluations | [10 empty] | GEO, GEOGLAM, National Intitutes, International Institutes, LP DAAC, USGS, NASA SERVIR
AJ. Product 13: GCAD four decades product release | [10 empty] | GEO, GEOGLAM, National Intitutes, International Institutes, LP DAAC, USGS, NASA SERVIR
AK. Product 14: Web\data portal development and data dissemination | [10 empty] | GEO, GEOGLAM, National Intitutes, International Institutes, LP DAAC, USGS, NASA SERVIR

## shell-cooperative-agreement
MILESTONES (Revised): Shell cooperative Agreement
Global Cropland Area Database at 30 m resolution (GCAD30) Project: June, 2013- May, 2018
NASA MEaSUREs
PI: Prasad S. Thenkabail. U. S. Gelopgical Survey, Flagstaff, AZ; pthenkabail@usgs.gov
Tel.: 928-380-9965
| 2013 | 2013-2014 | 2014 | 2014-2015 | 2015 | 2015-2016 | 2016 | 2016-2017 | 2017 | 2017-2018 | Comments
Key Milestones | 6/01/2013 to 08/31/2013 | 09/01/2013 to 02/28/2014 | 03/01/2014 to 08/31/2014 | 09/01/2014 to 02/28/2015 | 03/01/2015 to 08/31/2015 | 09/01/2015 to 02/29/2016 | 03/01/2016 to 08/31/2016 | 09/01/2016 to 02/28/2017 | 03/01/2017 to 08/31/2017 | 09/01/2017 to 05/31/2018
A. Establish contact with EOSDIS DAACs where products will eventually be archived. The DAAC for the project is: LP DAAC | [10 empty] | Ensure that necessary interface control documents* and operations agreements* are scheduled for development. The DAAC will initiate discussions about levels of service, data formats, potential user communities, identify issues unique to the data product/data set.
B. Define process for demonstrating utility of the project’s ESDRs to research community | [10 empty] | A brief report or white paper should be submitted to the NASA Program Manager.
C. Deliver Algorithm Theoretical Basis Documents to Program Scientist/Program Manager
D. Support community review of algorithms (led by Program Scientist) | [10 empty] | Program Scientists may hold a review meeting with peer reviewers nominated from the science and data management communities. This may consist of presentation(s) of a description of the algorithm theoretical basis and lineage steps at a scientific meeting/ workshop or a NASA community meeting established by the Program Scientist.
E. Provide an early sample of the data set, via a DAAC “sandbox” or PI’s website – with announcement for community availability for feedback, allowing time for users to comment.
F. Start production processing of ESDRs
G. Enter Directory Interchange Format (DIF) document(s) into Global Change Master Directory
H. Make data publicly available to users via MEaSUREs project's web site
I. EOSDIS DAAC(s) show links to MEaSUREs project's web site
J. Get data products certified by DAAC User Working Groups (DUWGs) and validated by the relevant HQ program scientist and the PE for DS | [10 empty] | DUWGs advise EOSDIS DAAC about relative priority of the data to be archived and distributed by them, and levels of service to be provided for the data commensurate with the DAAC’s budget.
K. Start migrating data products, processing source code, documentation, and ancillary data to appropriate EOSDIS | [10 empty] | By this time interface testing and end-to-end data flow tests should be completed between the MEaSUREs project and the DAAC.
L. DAAC(s) (upon start of production of final version of products)
M. Complete migrating data products to EOSDIS DAAC (s)
Reporting
N. Submit revised abstracts to e-Books | [10 empty] | NASA will set up e-Books with abstracts from proposals; Awardees submit revised abstracts reflecting negotiated CA's. NASA will also post the revised abstracts on a public web site similar to that for MEaSUREs 2006 projects (see http://earthdata.nasa.gov/our-community/community-data-system-programs/measures-projects)
O. Enter milestones in e-Books | [10 empty] | Milestones agreed to in CA
P. Quarterly reports (and updates to milestones) | [10 empty] | The frequency of reporting may be negotiated between the Program Manager and the PI.
Q. Initial entry to metrics page | [10 empty] | NASA will set up metrics web page to accept project metrics. Awardees sign-on to the web page and enter initial information and baseline comments to show when they would be ready to produce and distribute ESDRs to users.
R. Enter metrics | [10 empty] | Awardees enter metrics monthly after production and distribution of ESDRs commences
S. Submit product quality checklists
ESDSWG
T. Identify Working Group activities of interest and name participant(s) | [10 empty] | Program Manager may modify WG assignment to balance participation in WGs.
U. Participate in WG meetings/Telecons | [10 empty] | Activities vary from WG to WG. Some WGs schedule ad hoc meetings/telecons in frequently. Others have biweekly telecons
V. Participate in annual Joint Working Group meetings | [10 empty] | NASA organizes these meetings. They are generally held in October each year.